Version 2.0  |  April 2026  |  Prepared by Jera Consulting (Pty) Ltd	JC-SOP-SVC-001

# Service Delivery Operations Bible

Internal Governance Framework  |  JC-SOP-SVC-001  |  v2.0

## 1.  Purpose & Scope

This document is the single source of truth for how Jera Consulting manages all service delivery — from support vouchers to multi-million rand implementations. It defines thresholds, roles, communication rules, escalation paths, and governance for all four product lines: Sage Intacct, Sage X3, Sage 300 People, and SPA/VIP Payroll.

The framework is designed to run lean. It must work efficiently now and scale without structural change as the team and client base grow. Every rule here exists to reduce friction, protect delivery quality, and give leadership visibility without requiring their constant involvement.

RULE  Nothing moves from Sales to Ops without Proof of Payment (POP). No exceptions.

## 2.  Guiding Principles

- Async first — written updates, not meetings. Meetings are earned, not defaulted to.

- One POP trigger — no delivery work starts without proof of payment.

- Damian runs ops — Ryan's first point of contact is Damian. Always. Damian must know everything.

- Chalmain coordinates — she is the single handover point from Sales to Ops and owns the admin flow.

- Hypercare is a priority — clients in their first two years post go-live get elevated attention.

- Delegate with visibility — consultants own their delivery; managers own their product lines; Damian owns the whole picture.

- Escalate exceptions, not routine — if everything is running, nothing should reach Ryan or Raymond.

- Build for scale — processes set now must still work at 3x the volume without heroics.

## 3.  Team Structure & Roles

| Person | Title | Service Delivery Mandate |
| --- | --- | --- |
| JP Schmitt | AME Sales Director | Owns the commercial relationship and proposal. Hands over to Ops on POP. Chalmain has full view of his pipeline, meetings, and proposals. |
| Chalmain | Sales Secretary (JP) | Deal brief owner. Produces and distributes the deal brief. Schedules the internal brief meeting and the client kickoff. Single handover point from Sales to Ops. |
| Ryan de Kock | Business Development Director | Full view of all delivery. First escalation point above Damian. Attends all internal deal briefs. Signs off on major decisions. |
| Damian | Project Manager | Runs all ops-side delivery. Ryan's first point of contact. Chairs the internal deal brief. Owns project plans, kickoffs, escalations, and resource scheduling across all products. |
| Neo | Intacct Manager | Leads all Sage Intacct delivery. Attends internal briefs for Intacct deals. Manages Intacct consultants and client relationships. |
| Kevin | Sage X3 Manager | Leads all Sage X3 delivery. Signs off on all X3 resource allocation. Module-based task distribution across the team. |
| Melicke | Payroll Manager | Leads delivery for SPA, Sage 300 People, and VIP Payroll. Attends internal briefs for all payroll and HR deals. |
| Ben Oosthuizen | Finance | Invoicing, budget tracking, financial sign-off. |
| Raymond de Kock | Managing Director | Weekly RAG Teams message. Strategic oversight. Not in day-to-day delivery. |

NOTE  Damian is Ryan's first port of call on any ops question. Damian is expected to have full visibility across all active projects, all vouchers, and all product lines at any given time. If Damian does not know, that is an ops failure.

## 4.  Product & Deal Tier Classification

Every engagement must be classified by product and tier at intake. Tier determines governance, meeting requirements, PM involvement, and reporting obligations. The tables below define the tiers for each product line.

### 4.1  Sage Intacct

|  | VOUCHER | SMALL PROJECT | MEDIUM PROJECT | LARGE PROJECT |
| --- | --- | --- | --- | --- |
| License Value | — | < R165 000 | R165 001 – R300 000 | > R300 000 |
| Impl. Value | R4k – R50k (hrs) | R100k – R500k | R500k – R1.2M | R1.2M – R2M+ |
| Hours | 10 – 50 hrs | 100 – 350 hrs | 350 – 700 hrs | 700 hrs+ |
| Trigger | POP on voucher | Signed SOW + POP | Signed SOW + POP | Signed SOW + POP |
| PM | Damian (visibility) | Damian | Damian | Damian |
| Lead | Neo (allocates) | Neo | Neo | Neo |
| Kickoff | None (hypercare rules apply) | Client kickoff | Client kickoff | Client kickoff |
| Steering | None | Monthly 30 min | Bi-weekly 30 min | Weekly 30 min |
| Ryan Attends | CC on weekly RAG | CC on report | Internal brief + RAG | Internal brief + steering |

### 4.2  Sage X3

X3 is always a significant engagement. There is no small X3 project. The team aligns to every X3 implementation and tasks are distributed by module. Kevin signs off on all resource allocation.

|  | VOUCHER / SLA | STANDARD PROJECT | LARGE PROJECT |
| --- | --- | --- | --- |
| License Value | Existing client (SLA) | Any size | Any size |
| Impl. Value | SLA retainer / voucher | R300k – R1M | R1M – R2M+ |
| Hours | 10 – 50 hrs (SLA) | 300 – 700 hrs | 700 hrs+ |
| Resourcing | Kevin allocates per module | Kevin signs off — team aligned | Kevin signs off — full team |
| PM | Damian | Damian | Damian |
| Kickoff | None (SLA rules) | Client kickoff | Client kickoff + exec alignment |
| Steering | Monthly SLA review | Bi-weekly 30 min | Weekly 30 min |
| Ryan Attends | RAG only | Internal brief + RAG | Internal brief + steering |

### 4.3  SPA, Sage 300 People & VIP Payroll

SPA and VIP Payroll engagements are typically small and fast. Sage 300 People can be considerably larger depending on employee count and module scope. Melicke leads delivery across all three products.

|  | SPA / VIP (SMALL) | 300 PEOPLE (MED) | 300 PEOPLE (LARGE) | VOUCHER (ALL) |
| --- | --- | --- | --- | --- |
| License Value | ~R1k/month (10 emp) | < R165k | R165k – R300k+ | Existing client |
| Impl. Value | ~R4 000 (~1 day) | R60k – R160k | R160k+ | Voucher pack |
| Hours | 4 – 8 hrs | 60 – 150 hrs | 150 – 350 hrs | 10 – 50 hrs |
| PM | Damian (light touch) | Damian | Damian | Damian (visibility) |
| Lead | Melicke | Melicke | Melicke | Melicke allocates |
| Kickoff | None / quick call | Client kickoff | Client kickoff | None (hypercare rules) |
| Steering | None | Monthly 30 min | Bi-weekly 30 min | None |
| Ryan Attends | RAG only | CC on report | Internal brief + RAG | CC on weekly RAG |

### 4.4  Support Vouchers — All Products

Voucher packs are available in standard sizes of 10, 20, 30, and 50 hours. Custom amounts within this range are also available. Vouchers are sold through JP and purchased by the client. The Ops trigger is POP — not the signed agreement.

- Vouchers are allocated to the relevant product manager (Neo / Kevin / Melicke) who then assigns consultant time.

- Damian has full visibility of all active vouchers across all product lines.

- Clients in the 2-year hypercare window receive priority scheduling — see Section 8.

- Voucher balances are tracked in Odoo. Chalmain monitors usage and flags low balances for renewal conversations.

## 5.  Sales to Ops Handover — The POP Rule

The handover from Sales to Ops is triggered exclusively by Proof of Payment. The moment POP is confirmed, Chalmain initiates the flow below. This is non-negotiable — no resources are allocated and no delivery begins before this trigger.

| # | Step | Detail |
| --- | --- | --- |
| 1 | Deal Won — Sales | JP closes the deal. Proposal signed or verbal commitment confirmed. |
| 2 | Proof of Payment (POP) Received | POP is the trigger. Nothing moves to Ops without it. Chalmain confirms POP is in hand. |
| 3 | Chalmain Produces the Deal Brief | Short, factual, no fluff. See Section 6 for mandatory content. |
| 4 | Internal Deal Brief Meeting Scheduled | Chalmain sends meeting request with deal brief + proposal attached. Standard attendees: Ryan + Damian + relevant product manager. Consultant included if they were part of the sales process. |
| 5 | Internal Deal Brief Meeting | Damian chairs. Max 30 minutes. Output: resource allocated, kickoff date targeted, open questions resolved. |
| 6 | Chalmain Schedules Client Kickoff | Running parallel to Steps 3–5. Chalmain works the client's calendar so kickoff is ready to go immediately after the internal brief. |
| 7 | Client Kickoff | Damian leads. Presents the project plan and kickoff document. Sets the tone and expectations. |
| 8 | Project Delivery Begins | Consultant(s) execute. Damian maintains visibility. Chalmain monitors admin and milestones. |

NOTE  Chalmain schedules the client kickoff in parallel — she does not wait for the internal brief to complete before approaching the client's diary. The goal is to have a kickoff date ready to confirm at the end of the internal brief meeting.

## 6.  The Deal Brief

The deal brief is a short, factual document produced by Chalmain from JP's proposal, meeting notes, and her knowledge of the deal. It is not a summary of the proposal — it is the intelligence the ops team needs to deliver. It must be concise. One page is the target.

| Field | What to Include |
| --- | --- |
| Client & Product | Client name, product(s) being implemented, deal reference |
| Deal Value | License fee (ARR or once-off), implementation fee, total contract value |
| In Scope | Exactly what has been sold and committed to in the proposal |
| Out of Scope | Explicitly what is NOT included — prevents scope creep from day one |
| T&Cs — Make or Break | Any contractual clause, payment term, SLA, or condition that could affect delivery — flag it here |
| Client Vibe | Personality of the key stakeholder(s), decision-making style, any known sensitivities or concerns. Be honest. |
| Consultant Involved in Sales? | Yes / No — and if yes, who and what was discussed |
| Proposed Go-Live Date | Target date from the proposal or client expectation |
| Open Questions / Risks | Anything unresolved at handover that Ops needs to be aware of |

RULE  The deal brief must be attached to the internal meeting request before the meeting. Attendees are expected to have read it. The internal brief meeting is not a reading session.

## 7.  Meeting Framework

Meetings are the last resort, not the default. Every meeting below has a defined purpose, time limit, and mandatory output. No standing project meetings are permitted unless explicitly approved by Ryan.

| Meeting | Who Attends | When | Max Duration | Output |
| --- | --- | --- | --- | --- |
| Internal Deal Brief | Ryan + Damian + relevant product manager (+ consultant if in sales) | Within 48hrs of POP | 30 min | Resource allocated, kickoff date targeted |
| Client Kickoff | Damian + lead consultant + client stakeholders | Within 1 week of internal brief | 60–90 min | Project plan signed off, expectations set |
| Tier 3 Steering | Damian + client + product manager | Monthly | 30 min | Status confirmed, risks reviewed |
| Tier 4 Steering | Damian + Ryan + client + product manager | Bi-weekly | 30 min | Status, budget, timeline review |
| X3 Steering | Damian + Kevin + client | Bi-weekly | 30 min | Module progress, resource check |
| Escalation Call | Triggered parties only — see Section 9 | As triggered | 30 min max | Decision made, action logged |
| Raymond RAG Update | Automated Teams message — not a meeting | Weekly (Monday AM) | N/A | Red flags visible, no meeting needed |

### 7.1  Internal Deal Brief Meeting — Rules

- Ryan and Damian are always present.

- Only the relevant product manager attends — not all three.

- Consultant attends only if they were involved in the sales process.

- Damian chairs. Maximum 30 minutes.

- The deal brief and proposal must be read by attendees before the meeting.

- Output: resource named, kickoff date targeted, open questions documented.

### 7.2  Internal Meeting Cadence — Scale Trigger

Currently, internal deal brief meetings are scheduled per deal as required. As deal volume increases, the following model applies:

- Below 6 project starts per month: schedule individual briefs per deal, within 48 hours of POP.

- At 6 or more project starts per month: introduce a fixed weekly slot (e.g. Tuesday 9:00 AM) where all deals with POP that week are briefed in a single 45-minute session. This is standard practice at scale — one batch session prevents calendar fragmentation.

- Damian and Ryan review the cadence model at the 6-project-per-month threshold and agree the transition.

## 8.  Hypercare — The Two-Year Client Priority Framework

Every client is in hypercare for the first two years after their go-live date. During this period they receive elevated support priority, faster response SLAs, and closer monitoring. This is a Jera standard — not a premium option. Clients are experiencing our processes and our value during this window. We protect that.

| Period | Support Priority | Voucher Response SLA | Who Monitors |
| --- | --- | --- | --- |
| 0 – 3 months post go-live | CRITICAL — highest priority | Same business day | Damian + product manager |
| 3 – 12 months post go-live | HIGH | Next business day | Product manager |
| 12 – 24 months post go-live | ELEVATED | Within 2 business days | Product manager |
| 24 months+ | STANDARD | Standard SLA applies | Chalmain monitors |

- Chalmain tracks all client go-live dates in Odoo. Hypercare status is visible on the service dashboard.

- When a hypercare client logs a voucher request, it is flagged automatically and prioritised above standard queue.

- At the 24-month mark, Damian and the relevant product manager review the client relationship and flag any renewal or upsell opportunities to JP.

## 9.  Escalation Framework

Escalation is the system working correctly. Surface problems early. The table below defines every trigger, threshold, escalation path, and response SLA.

| Trigger | Threshold | Escalate To | SLA | Method |
| --- | --- | --- | --- | --- |
| Budget overrun | > 10% of agreed value | Damian → Ryan | 24 hrs | Email |
| Timeline slip | > 2 weeks behind plan | Damian flags to Ryan | 24 hrs | Email |
| Major timeline slip | > 4 weeks | Damian + Ryan → client | 24 hrs | Call |
| Client complaint / red flag | Any formal complaint | Chalmain → Ryan immediately | Same day | Call |
| Consultant unavailable | > 2 days mid-project | Damian → Kevin/Neo/Melicke | Same day | Teams/call |
| Scope change requested | Any change to agreed scope | Chalmain issues CRF → Damian signs off | 48 hrs | Email + CRF doc |
| Unpaid invoice blocking delivery | > 30 days overdue | Chalmain → Ben + Ryan | 24 hrs | Email |
| Hypercare SLA breached | Response outside SLA window | Damian notified immediately | Same day | Teams |
| X3 resource conflict | Module resourcing issue | Damian → Kevin | 24 hrs | Teams or call |

### 9.1  Escalation Protocol

- Chalmain or Damian identifies that a trigger threshold has been breached.

- Written escalation sent to the relevant person(s) via email or Teams — clearly flagged.

- If no response within SLA, follow up via Teams or WhatsApp.

- If still no response, call directly.

- Resolution confirmed in writing. Chalmain logs the escalation, response, and outcome in Odoo.

## 10.  RACI — Roles & Accountability

R = Responsible (does it)   |   A = Accountable (owns the outcome)   |   C = Consulted   |   I = Informed

| Activity | Chalmain | Damian | Neo (IC) | Kevin (X3) | Melicke (Pay) | Ryan | Raymond |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Deal brief production | R | I | — | — | — | I | — |
| Internal brief scheduling | R | A | C | C | C | I | — |
| Internal brief (chair) | A | R | C | C | C | I | — |
| Client kickoff scheduling | R | A | — | — | — | — | — |
| Client kickoff (lead) | C | R | C | C | C | I | — |
| Project plan production | — | R | C | C | C | I | — |
| Resource allocation (IC/Pay) | — | R | A | — | A | I | — |
| Resource allocation (X3) | — | C | — | R/A | — | I | — |
| Status reporting | C | R | C | C | C | I | I |
| Budget tracking | R | A | — | — | — | I | I |
| Escalation triage | R | A | C | C | C | I | — |
| Invoice triggering | R | C | — | — | — | — | C |
| Scope change (CRF) | R | A | C | C | C | I | — |
| Hypercare monitoring | R | A | C | C | C | I | — |
| CoB process (pre-transfer) | R | I | — | — | — | I | — |
| Weekly RAG report | R | A | C | C | C | I | I |
| Project closure | R | R | C | C | C | I | — |

## 11.  Change of Business Partner (CoB) Process

A CoB engagement moves through Sales until the VAR-to-VAR transfer is complete. Jera has no system access until that transfer is confirmed by Sage. The process is tracked by Chalmain and handed to Ops at the point of transfer completion.

| # | Stage | Detail / Rules |
| --- | --- | --- |
| 1 | Deal agreed in Sales | JP and client agree to partner transfer. Chalmain tracks in pipeline. |
| 2 | VAR-to-VAR Transfer initiated | Sage initiates the transfer between outgoing and incoming partner. Jera has NO system access until complete. |
| 3 | Sales may request consultant support | Consultants may assist with pre-transfer questions or scoping. This is informal — no project opened, no ticket. Damian is aware. |
| 4 | VAR-to-VAR Transfer confirmed | Jera receives confirmation. System access granted. This is the trigger to open a formal project or support record. |
| 5 | POP received (if applicable) | If implementation or support is part of the deal, POP triggers the standard Sales-to-Ops flow from Section 5. |
| 6 | Standard flow applies | Deal brief, internal brief, kickoff — all as per normal process. |

RULE  No formal project is opened and no delivery work begins until the VAR-to-VAR transfer is confirmed. Consultants may provide informal pre-transfer support at the request of Sales, but this is tracked and Damian is aware.

## 12.  Audit-Led Engagement Process

Some client engagements begin with an audit — either a free discovery exercise or a fixed-price engagement — before a full implementation SOW is scoped. The audit is a Sales and Ops collaboration; the resulting project follows the standard flow.

| # | Stage | Detail / Rules |
| --- | --- | --- |
| 1 | Audit engagement agreed | Audit is either free or fixed price — agreed at proposal stage. Chalmain tracks. |
| 2 | POP received (if fixed price) | Fixed-price audits require POP before work starts. Free audits proceed on written agreement. |
| 3 | Audit delivered | Consultant(s) execute the audit. Damian has visibility. No formal project governance required unless > 50 hours. |
| 4 | Audit output produced | Findings document delivered to client. This becomes the foundation of the SOW. |
| 5 | Joint SOW — Sales + Ops | Ryan + relevant product manager work with JP to scope the hours and produce the SOW. Chalmain coordinates the document flow. |
| 6 | Proposal presented by Sales | JP presents the proposal to the client. Standard commercial process. |
| 7 | POP received — standard flow | On POP, the deal follows the standard Sales-to-Ops flow from Section 5. |

## 13.  Client Kickoff Document — Mandatory Content

Damian presents a single kickoff document at every client kickoff. The project plan is a separate attachment. The kickoff document must contain the following as a minimum — no ambiguity, no gaps.

| Section | What Must Be Included |
| --- | --- |
| Project Overview | Client name, product, project code, go-live target date, project manager, lead consultant |
| Confirmed Scope | What is being implemented — modules, entities, integrations, data migrations. Signed off on the day. |
| Explicitly Out of Scope | What is NOT included. Non-negotiable to have this in writing at kickoff. |
| Project Plan Summary | High-level milestones, phases, and target dates. Full plan shared as a separate document. |
| Resource Allocation | Who from Jera is doing what. Who from the client is the project owner and key contact. |
| Communication Plan | How and when Jera and the client communicate. Channels, cadence, escalation contacts. |
| Key T&Cs | Payment terms, change control process, sign-off requirements. No ambiguity. |
| Client Responsibilities | What the client must do and when — data, access, UAT, sign-offs. Delays here affect go-live. |
| Risk Register (initial) | Any known risks at kickoff — data quality, resource availability, integration dependencies. |
| Sign-Off Block | Client project owner signs the kickoff document on the day. This is not optional. |

RULE  The client project owner signs the kickoff document at the kickoff meeting. A kickoff that ends without a signature is not complete. Chalmain follows up within 24 hours if the signature is not obtained on the day.

## 14.  Raymond's Weekly RAG Report

Raymond receives a weekly Teams message every Monday morning. This is not a meeting. It is a structured status summary that gives him full visibility across all delivery and all teams without requiring his time or attendance anywhere.

### 14.1  RAG Status Definitions

- GREEN — On track. No action required.

- AMBER — At risk. Being managed. Raymond is aware but no action required from him yet.

- RED — Escalation active or imminent. Raymond may be asked to act.

### 14.2  Weekly RAG Message Structure

The message follows this structure every week:

- Active Projects by Product — RAG status per project (name, tier, status, one-line note if AMBER or RED)

- Active Vouchers — count per product line, any hypercare flags

- New Projects Started This Week — name, product, tier

- Projects Closed This Week — name, product

- Open Escalations — count, highest severity

- Invoices Triggered This Week — total value

- Any item requiring Raymond's input or awareness — clearly flagged at the top

Chalmain produces the RAG message from the Odoo dashboard. Damian reviews and approves before it is sent. Ryan is copied.

## 15.  Document Control

This framework is reviewed every six months or when team size, product set, or delivery volume changes materially. Damian and Ryan lead the review. Raymond approves any structural changes.

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | April 2026 | Ryan de Kock | Initial draft |
| 2.0 | April 2026 | Ryan de Kock | Product tiers, deal flow, hypercare, CoB, audit-led, full team structure |